FY26 Recovery Housing Program Performance Report & Notice of Public Hearing – 10/1/25-9/30/26
Financials
	Service Provider
	Total Award Amount
	Total Expended during Reporting Period
	Total Expended to Date

	Endorphin Power Company
	$693,200.00
	$0.00
	$332,835.61

	Hozho Center for Personal Enhancement
	$969,499.00
	$152,301.34
	$731,099.15

	New Mexico Reentry Center
	$1,000,000.00
	$273,892.34
	$792,657.31

	TenderLove Community Center
	$1,200,000.00
	$560,414.19
	$1,200,000.00

	Crossroads for Women (award recaptured 8/1/25)
	$600,000.00
	Award Recaptured
	-

	The Santa Fe Mountain Center
	$644,986.47
	-
	-

	Cornerstone Community Solutions
	$400,000.00
	-
	-

	Espanola Pathways Shelter
	$561,577.86
	-
	-

	Golden Forward, Inc
	$309,593.50
	-
	-

	Serenity Mesa
	$773,983.76
	-
	-

	Supporting People in Need
	$122,000.00
	-
	-


Narratives
October 30, 2024 – Annual Reporting
As of October 30, 2024, Housing New Mexico has awarded a total of $3.7 million of New Mexico's RHP allocations to five approved recipients. After a period of 6 months, one of the awards was respectfully returned due to executive staff turnover experienced by Crossroads for Women.
Of the remaining four awards, one is fully drawn and has experienced a complete loss of their facility due to fire in January 2024. The project was at a point where the rehabilitation of a sixteen- unit multi-family property had completed 50% of the units to place in service. Now, they are working with the insurance company to settle their total loss claim and will repay funds to the RHP based on the amounts paid by the insurance, covering the superior mortgage first, then the balance to Housing New Mexico. Housing New Mexico is working to recapture the $600,000 award and include these recaptured funds in an amended NOFA. Housing New Mexico intends to allocate all RHP funds by March 2026.
•	Hozho Center for Personal Development: The acquisition and rehabilitation are complete. As of the reporting date, 75.4% of the awarded funds have been drawn, and the recovery housing has been put into service on January 2025. The center is currently servicing twelve individuals to meet a 12-person capacity. In August of 2026, Hozho Center relocated to a new office space in Downtown Gallup, to serve more individuals in need and conduct street outreach.
•	New Mexico Reentry Center: In March of 2025, New Mexico Reentry Center secured the acquisition of a new recovery household. To date, New Mexico Reentry Center has served 113 individuals, provided rental assistance on 95 different occasions, and has helped 11 individuals transition into permanent housing. To date, New Mexico Reentry Center has expended 77.4% of their total award.
Awards – December 2024
TenderLove Community Center
•	Award: $1,200,000.00
•	Project Description: TenderLove Community Center is an existing recovery housing provider that has provided Recovery Housing for 160 individuals since receiving this award. TenderLove Community Center has finalized the purchase of a second recovery house as of August 2025. Through the help of this program, TenderLove Community Center has seen 129 individuals transition to permanent housing. To date, TenderLove Community Center has spent 100% of their total award.
Endorphin Power Company
•	Award: $693,200.00
•	Project Description: Endorphin Power Company aims to increase service capacity by providing housing for 10 additional individuals in one-bedroom units and additional units for family reunification. In March of 2025, Endorphin Power Company finalized the purchase of a new recovery household. Six individuals have been admitted to the program, beginning in May of 2025, and 48% of the total award has been expended.
These two awards fully allocate RHP funding through FY2023. 
Notice to Citizens and Public Comment Period
A Public Comment Period began on September 30th, 2025. The Public Notice and FY25 Performance Report were published in September, in 6 newspapers across the State of New Mexico, and on both the Housing New Mexico and Department of Finance and Administration’s websites. A Public Hearing was held virtually on October 14th. No comments were received during the Public Comment Period. Affidavits of the Publication have been obtained.
October 30, 2025 – Annual Reporting & New Awards
As a result of the approval of the FY25 Action Plan and NOFA amendments, Housing New Mexico followed the Citizen Participation Plan process to ensure that information was available regarding the timeline for applying. Housing New Mexico received seven RHP NOFA applications. Six applicants reached the threshold for receiving an award, while one did not fit the criteria. RHP contracts were executed in July 2026. Housing New Mexico provided training and support to all RHP providers in order to comply with federal grant regulations and conducted an onboarding training for all new providers. All four original service providers were monitored for compliance with 2 CFR 200 and all RHP regulations during the reporting period.
These six awards fully allocate RHP funding through FY2025.
Notice to Citizens and Public Comment Period
A Public Comment Period will begin on September 28th, 2026. The Public Notice and FY26 Performance Report will be published on September 28, in 6 newspapers across the State of New Mexico, and on both the Housing New Mexico and Department of Finance and Administration’s websites. A Public Hearing will be held virtually on October 14th at 2:00pm. All comments received during the Public Comment Period and Public Hearing will be addressed and documented. Affidavits of the Publication will be obtained.
Recovery Housing Program – Next Steps
Upon execution of the FY26 RHP Grant Agreement between the State and the Department of Housing and Urban Development, and the execution of the RHP Grant Agreement between the State and Housing New Mexico, Housing New Mexico will open a Notice of Funding Availability to elicit qualified applicants for the Recovery Housing Program in order to allocate all FY26 RHP funds.
Conclusion
The Recovery Housing Program has made meaningful progress in meeting the needs of individuals impacted by substance use disorders in New Mexico. Despite challenges such as the return of funds and unexpected project delays, Housing New Mexico remains committed to ensuring the successful deployment of RHP funds.
Measures
	Accomplishments
	Projected
	This Report Period
	To Date

	Performance Measure
	
	
	

	Facility or Group Home
	15
	3
	5

	Increased Residential Capacity as #of beds
	86
	33
	110

	# of persons that transitioned to permanent housing
	80
	45
	45

	#of persons with additional disability
	86
	45
	45

	# of Section 3 Labor Hours
	0
	0
	0

	# of Targeted Section 3 Labor Hours
	0
	0
	0

	# of Total Labor Hours
	0
	0
	0



	Performance Measure
	Projected
	This Report Period
	To Date

	# of Housing Units
	4
	3
	4

	# of Multifamily Units
	2
	1
	2

	# of Single-family Units
	2
	0
	0



	Beneficiaries
	Projected Total
	Projected Low
	Projected Mod
	This Report Period Total
	This Report Period Low
	This Report Period Mod
	To Date Total
	To Date Low
	To Date Mod

	Performance Measure
	
	
	
	
	
	
	
	
	

	# of Persons
	150
	150
	0
	68
	68
	0
	217
	217
	0



	Race/Ethnicity
	Owner Total
	Owner Hispanic/Latino
	Renter Total
	Renter Hispanic/Latino
	Household/Persons Total
	Household/Persons Hispanic/Latino

	Direct Benefit – This Report Period
	0
	0
	0
	0
	68
	0

	Direct Benefit – To Date
	0
	0
	0
	0
	217
	0




